## Project Plan and Gantt
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
Safe Living | Weicong Feng | 2019-02-01 | 2019-04-30 |  | 20%
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
Safe Living Feasibility Analysis | Weicong Feng | 2019-02-01 | 2019-02-06 | 5 | Complete
Set Kick-Off Meeting | Soon Chun | 2019-02-07 | 2019-02-07 | 0 | Complete
Architecture Design | Weicong Feng | 2019-02-08 | 2019-02-16 | 8 | Complete
LAMP Serveres Setup | Weicong Feng | 2019-02-09 | 2019-02-16 | 7 | Complete
Crime & House DB Development | Weicong Feng | 2019-02-13 | 2019-02-18 | 5 | Complete
Individual & Organization UI Design | Weicong Feng | 2019-02-17 | 2019-02-20 | 3 | Complete
Approve Meeting | Soon Chun | 2019-02-21 | 2019-02-21 | 0 | Complete
Logical Control Development | Weicong Feng | 2019-02-22 | 2019-03-07 | 13 | In Progress
Visualization Improvement | Weicong Feng | 2019-03-08 | 2019-03-20 | 12 | Not Started
Unit Testing | Weicong Feng | 2019-03-21 | 2019-03-27 | 6 | Not Started
Process Optimization | Weicong Feng | 2019-03-28 | 2019-04-03 | 6 | Not Started
UI Optimization | Weicong Feng | 2019-04-04 | 2019-04-11 | 7 | Not Started
Security Optimization | Weicong Feng | 2019-04-12 | 2019-04-18 | 6 | Not Started
System Testing | Weicong Feng | 2019-04-19 | 2019-04-25 | 6 | Not Started
Document | Weicong Feng | 2019-04-26 | 2019-04-30 | 4 | Not Started
LAUNCH |  | 2019-02-01 | 2019-04-30 | 88

## Project Plan and Gantt - BLANK
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Overdue
|  |  |  | 0 | In progress
|  |  |  | 0 | In progress
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
0
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Stakeholder List
STAKEHOLDER LIST
NAME | POSITION | ROLE IN PROJECT | EMAIL ADDRESS | REQUIREMENTS | EXPECTATIONS
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
COST BASELINE
ITEM / TASK | % COMPLETE | BASE COST | COST | ACTUAL COST | % BUDGET SPENT
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
COMMUNICATION PLAN
COMMUNICATION TYPE | DELIVERABLE | DESCRIPTION | DELIVERY METHOD | FREQUENCY | OWNER | AUDIENCE
Presentation | 15-minute PowerPoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.